## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Creating Project Folder Structure | 1 | 2023-11-07 | Created the folder structure of the Vue App.
Creating basic structure of project itself | 3 | 2023-11-10 | Started creating all the files needed for the project and started working with components.
Continue working on houseList and filterComponent | 1 | 2023-11-12 | Continued working on filterComponent, houseList and homeView to make evertything work as expected.
Continue working on houseList and HomeView | 2 | 2023-11-15 | Fixing errors that were causing things to render incorrectly. Also added button for sorting.
Working on sorting and filtering | 1 | 2023-11-16 | Fixing some bugs that caused the site to be unable to sort or filter houses based on the users input.
Adding create new button and page | 3 | 2023-11-17 | Adding button for creating new house, also added the page where you can create that new house.
Creating form page where you can create and edit houses | 1 | 2023-11-20 | Adding page for creating and editing houses, if you have the correct permissions
Working more on the formpage, making it safer and easier to use | 2 | 2023-11-21 | Continued working on the form for the houses to make it work like you would expect. Removed some bugs too.
Working on detail page where you can show off your house | 4 | 2023-11-22 | Created the detail page for showing houses and removed some bugs from the form component
Working on formpage and detail page and inplemented the EditView | 5 | 2023-11-23 | Contiue working on detail page, formpage and inplemented a new feauture for editing houses that actually edits the house
Inplemented all of the mobile requirements using css | 3 | 2023-11-24 | Made the whole site mobile responsive and got some icons of internet for the Listings and Favorites pages. Due to them being from the internet, the color doesn't completely match, but it is still a shade of orange.
Added bonus point: Implement favorites into the website | 3 | 2023-11-24 | Added the feautue that you can now add a house to your list of favorites, so that you can keep it and show it to your friends | x
Added bonus point: Add history to the website | 3 | 2023-11-25 | Added history to the website so the user can see what they saw in the past, limits to 5 so it won't take up the whole screen | x
Added bonus point: Add a about page in the website for some background | 1 | 2023-11-29 | Added the about page as a bonus point, quite easy, just a simple screen of tekst and a little image | x
Added bonus point: Add recommendations to the detail page so user has options | 6 | 2023-11-30 | Added a component to the detial page that will give a few options out as a recommendation | x
Fixed error regarding formCpomponent and changed components names | 1 | 2023-12-13 | Fixed error that meant tht editing was disabled, changed xomponents names and removed unused variables
Fixing erorr with formComponent and updated the API part of the site | 4 | 2023-12-18 | Fixed error of editing part that came back, also removed the data.vue and added API.js
Changed all the API calls from using the methods in vue to use the js file | 2 | 2023-12-19 | Changed API calls to use the js file instead of the vue file
Fixed error with showing houses as a card and in detail form | 1 | 2023-12-20 | Changing the way empty housenumberAdditions are treated inside the website
Fixing styling errors that came up by changing the way that the websites worked | 1 | 2023-12-21 | Fixed the bugs that showed on the screen due to it being different then first, Including formComponent and other files
Total amount of hours | 35